## Product Backlog
Product Name: | C1325 Library Management System | [5 empty] | Complete Fields in Green!!!
Team ID:
Name: | Henry Bang
Initials: | HB
Student ID: | 1001502505
Teaming is not available for this assignment!
Optional teaming may be available in future assignments
| Remaining | Completed (this sprint)
Total Features | 19 |  | Total
Sprint 1 Left | 14 | 5 | 1
Sprint 2 Left | 7 | 7 | 2
Sprint 3 Left | 6 | 1 | 3
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority |  | Planned | Status | As a... | I want to... | So that... | Notes
AP | 1 |  | 1 | Finished in Sprint 1 | Librarian | Add a publication | I can keep track of what is in the library
LP | 2 |  | 1 | Finished in Sprint 1 | Librarian | List all publications | I can find out what is in the library | This will also be needed for the next two features
CO | 3 |  | 1 | Finished in Sprint 1 | Librarian | Check out a publication | I can track who has borrowed each publication | Each publication will need to know if it is checked out or not
CI | 4 |  | 1 | Finished in Sprint 1 | Librarian | Check in a publication | I can tell when a publication is returned
HE | 5 |  | 1 | Finished in Sprint 1 | Librarian | Get help | I can learn how to use the system
PA | 6 |  | 1 |  | Librarian | Add a patron | I can conveniently keep track of all patrons | This is the Bonus level for Sprint #1
SP | 7 |  | 1 |  | Librarian | Select a patron when checking out a pub | I don't have to rekey recurring patron info | This is the Bonus level for Sprint #1
DMM | 8 |  | 2 | Finished in Sprint 2 | Librarian | Use a standard dialog for the main menu | I can interact more naturally with the system
DNP | 9 |  | 2 | Finished in Sprint 2 | Librarian | Use a series of dialogs for a new publication | I can interact more naturally with the system
DLP | 10 |  | 2 | Finished in Sprint 2 | Librarian | Use a stand dialog for the list of publications | I can interact more naturally with the system
DH | 11 |  | 2 | Finished in Sprint 2 | Librarian | Use dialogs for all other interaction (e.g., help) | I can interact more naturally with the system
DCO | 12 |  | 2 | Finished in Sprint 2 | Librarian | Use dialogs for check in and check out | I can interact more naturally with the system
DRM | 13 |  | 2 | Finished in Sprint 2 | Librarian | Add rich text to the main menu (dialog) | The menu is easier to navigate | This is the Bonus level for Sprint #2
DRH | 14 |  | 2 | Finished in Sprint 2 | Librarian | Add rich text to the help dialog | The help text is easier to understand | This is the Bonus level for Sprint #2
DCP | 15 |  | 2 |  | Librarian | Use a custom dialog to create new pubs | I can create them more quickly | This is the Extreme Bonus level for Sprint #2
MW | 16 |  | 3 | Finished in Sprint 3 | Librarian | Interact with a main window with drop-down menus | I can interact more naturally with the system | Replace the main menu dialog with a main window that is always visible
MT | 17 |  | 3 | In Work | Librarian | Add a toolbar to the main menu | I can more quickly access common features | This is the Bonus level for Sprint #3
MP | 18 |  | 3 |  | Librarian | Add a scrolling publications table to main window | I can more quickly look up publications | This is the Extreme Bonus level for Sprint #3
CU | 19 |  | 1 |  | Librarian | Add custom info for each publication type | I can keep better track of library assets | This is the Extreme Bonus level for Sprint #1

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2017-09-21 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-09-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 6
Day 1 Left | 6 | 0
Day 2 Left | 6 | 0
Day 3 Left | 6 | 0
Day 4 Left | 6 | 0
Day 5 Left | 6 | 0
Day 6 Left | 6 | 0
Day 7 Left | 6 | 0
| Feature ID |  | Description | Status | Notes
| AP |  | Create a Publication class with data and a constructor |  | Included a WRITTEN test with each constructor and method!
| AP |  | Add the to_string method to Publication
| AP |  | Add the is_checked_out method to Publication
| AP |  | Add the check_out method to Publication
| AP |  | Add the check_in method to Publication
| LP |  | --> Add additional tasks to complete the homework
CO
CI
HE
PA
SP
CU

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2017-09-28 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-10-05
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
| Feature ID |  | Description | Status | Notes
| DMM |  | --> Add all tasks needed to complete the homework |  | Included a WRITTEN test with each constructor and method!
DNP
DLP
DH
DCO
DRM
DRH
DCP

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2017-10-05 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2017-10-12
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
| Feature ID |  | Description | Status | Notes
| MW |  | --> Add all tasks needed to complete the homework |  | Included a WRITTEN test with each constructor and method!
MT
MP